## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME: | Fresher_DataAnalysis_Python
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-07-07
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Fresher_DataAnalysis_Python |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IAC IP23
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2024-07-03 | Data Cleaning Complexity | Project Planning and Execution | Yes | Allocate more time initially for thorough data profiling and cleaning. Anticipate and plan for unexpected data inconsistencies that may require iterative cleaning processes. | Utilized Python libraries such as Pandas for data loading, cleaning, and preprocessing. | Self(Aritra Sarkar) | SOLVED | Implemented data profiling techniques to identify missing values, outliers, and inconsistencies.
2 | 2024-07-05 | Iterative Analysis and Visualization | Data Analysis and Visualization | No | Plan for iterative cycles in analysis and visualization to accommodate stakeholder feedback and ensure visualizations effectively convey insights. Allocate sufficient time for refinement and iteration based on initial drafts. | Employed Python visualization libraries like Matplotlib and Seaborn to create initial drafts of visualizations (e.g., scatter plots, bar charts). | Self(Aritra Sarkar) | SOLVED | Conducted iterative data analysis using Python, including descriptive statistics, correlation analysis, and regression modeling where applicable
3 | 2024-06-24 | Documentation Integration | Project Documentation | Yes | Integrate documentation milestones with analysis phases from the project's outset. Ensure consistent updates to documentation throughout the project to avoid last-minute rushes and discrepancies. | Integrated documentation milestones with Python code repositories (e.g., using Jupyter Notebooks, Markdown) to maintain transparency and facilitate version control. | Self(Aritra Sarkar) | SOLVED | Ensured consistency between Python scripts, analysis outputs, and documentation formats throughout the project lifecycle.
4 | 2024-07-07 | Predictive Modeling Potential | Future Scope | No | Explore incorporating predictive modeling techniques in future iterations to forecast long-term student outcomes and market trends. Invest in advanced machine learning skills and data collection strategies to support predictive modeling efforts effectively | Documented Python code and methodologies used for predictive modeling to support future enhancements and iterations. | Self(Aritra Sarkar) | SOLVED | Explored Python libraries like Scikit-learn for building predictive models (e.g., linear regression).
5 | 2024-06-20 | Stakeholder Communication | Stakeholders | No | Establish regular communication channels with stakeholders to gather feedback early and often. Ensure presentations and demos are rehearsed thoroughly to align with stakeholder expectations and facilitate clear, concise delivery of findings. | Prepared presentation materials using Python-based tools (e.g., creating slides with Matplotlib, Seaborn, or exporting data visualizations to presentation software). | Harshada Topale | SOLVED | Incorporated Python-generated charts and graphs into presentations to visually support findings and facilitate stakeholder understanding.